REQUEST FOR TENDER

For

asphalt & spray seal projects

and

periodic supply & placement

of asphalt & spray seals

2019/20

For

CITY OF DARWIN

CONTRACT NO: 					2019-058

COUNCIL’S CONTACT OFFICER: 		FERDINAND ORIAN

TELEPHONE:						08 8930 0695

TENDER CLOSING INFORMATION:

TIME: 2PM						DATE: 1 AUGUST 2019

## All tenders for this Contract must be lodged through the City of Darwin electronic tender portal www.tenderlink.com/darwin.

Document Date: 11 July 2019

This Page Left Intentionally Blank

These Tender Documents and Specification comprise the following sections:

SECTION	SUBJECT

1.00	CONDITIONS OF TENDERING

2.00	SPECIAL CONDITIONS OF CONTRACT

3.00	GENERAL CONDITIONS OF CONTRACT

4.00	ANNEXURE

5.00	PRELIMINARY CLAUSES

6.00	TECHNICAL SPECIFICATION

7.00   	TENDER DOCUMENTS

8.00			ATTACHMENTS

9.00			APPENDIX

This Page Left Intentionally Blank

###### SECTION 1.00

CONDITIONS OF TENDERING

SECTION 1.00	CONDITIONS OF TENDERING

SECTION		SUBJECT

  - REQUEST FOR TENDER

1.2			NATURE OF CONTRACT

1.3			PERIOD OF CONTRACT

1.4			TENDER DOCUMENTS

1.5			TENDER ENQUIRIES

1.6			CANVASS OF LORD MAYOR AND ALDERMEN

1.7			PROBITY OF TENDER PROCESS

1.8			TENDERER TO BE FULLY SELF INFORMED

1.9			SUBMISSION OF TENDERS

1.10			DOCUMENTS TO BE LODGED WITH TENDER

1.11			LODGEMENT OF TENDERS

1.12			CLOSING OF TENDER BOX

1.13			FACSIMILE TENDERS

1.14			OPENING OF TENDERS

1.15			INFORMAL TENDERS

1.16			TENDER VALIDITY PERIOD

1.17			ALTERNATIVE PROPOSALS

1.18			CUSTOMS DUTIES

1.19		DISCREPANCIES, ERRORS AND OMISSIONS IN TENDER   DOCUMENTS

1.20			ASSESSMENT OF TENDERS

1.21			QUALITY SYSTEMS

1.22			ACCEPTANCE OF TENDERS

1.23			INSURANCE

1.24			PRICE VARIATION

1.25			INTERPRETATION OF TERMS

1.     	CONDITIONS OF TENDERING

## REQUEST FOR TENDER

The Invitation to Tender is not an offer; it is merely an invitation to negotiate with any person who submits a bid.  The submission of a tender does not create a contract between any Tenderer and the Principal.

## NATURE OF CONTRACT

The contract shall be a Schedule of Rates contract and shall not be subject to adjustment for rise and fall in costs. The Tenderer shall complete each Schedule and lodge same with the tender. All tendered prices are to include but not limited to GST.

## PERIOD OF CONTRACT

Refer to Section 5 Clause 5.2 Construction Program.

## TENDER DOCUMENTS

The Tender Documents shall be the Form of Tender, Conditions of Tendering, Special Conditions of Contract, and General Conditions of Contract AS4000-1997, Annexure, and such Specifications, Schedules, Drawings and other documents as are issued by the City of Darwin for the purpose of tendering.

No explanation or amendment to the tender documents shall be recognised unless in the form of a written addendum thereto issued by the City of Darwin.

## TENDER ENQUIRIES

Any enquiries relating to this Contract should be referred to the Contract Administrator on telephone (08) 8930 0695.

## CANVASS OF LORD MAYOR AND ALDERMEN

Any Tenderer, or agent acting on his behalf, canvassing the Lord Mayor, Aldermen or City of Darwin staff with respect to the preparation, lodgement or assessment of his tender shall have that tender automatically disqualified and rejected.

## PROBITY OF TENDER PROCESS

A Statutory Declaration is included in the Tender Documents which addresses “Collusive Tendering”.  Such declaration must be made and returned as part of the Tender.

## TENDERER TO BE FULLY SELF INFORMED

A Tenderer is required to acquaint himself with all conditions relating to the Tender and to inspect the site prior to submitting his Tender.

If a Tenderer has any doubts as to the meaning of any portion of the Tender Documents he shall seek clarification from the officer listed in Clause 1.5.

Any clarification given pursuant to this clause may also be issued to all other prospective Tenderers.

## SUBMISSION OF TENDERS

At time of tendering, all Tenderers must submit evidence to satisfy the Superintendent of his ability to undertake the work successfully and to establish that he has adequate experience, facilities, organisation, labour, equipment and financial resources to cope with the nature of extent of the work outlined in this specification.  Only Tenderers who are able to satisfy the Superintendent in this regard will be considered.

The tender shall be submitted upon the Form of Tender provided.

The tender shall set forth the full Christian names, surname and address of the Tenderer – if a person.  When the tender is by a firm, it shall set forth the names in full of each member of the firm.  When the tender is by a Company, there shall be set forth the name of the Company and the address for the service of notices for the purposes of this tender and any subsequent contract arising out of acceptance of the tender.

The tender shall be accompanied by any other documents required by the tender documents to be submitted with the tender, including but not necessarily limited to the provision of a bankers reference and two (2) business references.

The Tenderer shall sign the tender or if the Tenderer is a Corporation, affix common seal in the manner prescribed by its articles of association or otherwise appropriately and formally have the tender signed and signature witnessed.

The documents referred to in the above paragraphs shall be completed in full by the Tenderer.

The tender shall be for the whole of the Works unless otherwise stated in the Tender Documents.

The Tenderer shall not alter or add to any Tender Document except as required by these Conditions of Tendering.

## DOCUMENTS TO BE LODGED WITH TENDER

Tenderers shall lodge the following documents with their   tender:

- Form of Tender

- Schedule of Insurance

- Quality Assurance

- Declaration of Business Status

- Summary of Business Capabilities

- Schedule of Plant & Equipment. Include detailed photographs taken in the last

3 months

- Qualifications & Licences

- Schedule of Sub Contractors, including nominated electrical subcontractor for traffic signal detector loop installation works.

- Schedule of Suppliers

- Schedule of Current Commitments, including any Commitments within this Contract period

- Schedule of Financial & Trade Referees

- Declaration of Supporting Information

- Company Search

- Bankruptcy Clearance Search

- Conformity to Specification

- Occupational health and Safety Policies and Procedures

- Schedule of Rates

- Collusive Tendering - Statutory Declaration

- Presentation of a Local Industry Participation Plan (LIPP)

- Statement of methodology and works program to demonstrate the meeting of each of the separable portions’ practical completion.

- Statement of Contractor’s capabilities and CVs of key personnel.

- Seal designer’s current Statement of Attainment of AAPA’s course titled “Sprayed Sealing Selection and Design” obtained within three (3) years if the date of submission of the tender.

Any tender that is not accompanied by completed documents required under this clause may be rejected.

1.10.1	Company Bankruptcy Searches

The Tenderer shall provide to Council, a Current Company Search.  The company search is to be undertaken within two weeks prior to tender closing date.

The Tenderer shall provide to Council, a Bankruptcy Clearance Search for each Director of the Company.

To obtain these searches contact:

- Australian Business Research – phone: 07 3837 1333 or 1300 366 402

- Website address: www.abr.com.au

# 1.11	LODGEMENT OF TENDERS

## All tenders for this Contract must be lodged through the City of Darwin electronic tender portal www.tenderlink.com/darwin.

The size of the files you wish to transfer will determine how long it takes to make a submission.

All suppliers will receive a reminder email 24 hours before the ERFX is due to close. It is critical that all suppliers are aware of the information contained in this clause

To make an electronic submission you must:

- Ensure ALL files are uploaded to the Electronic Tenders Box (ETB) PRIOR to the closing time and date. PLEASE NOTE: The ETB closes automatically at this time. File transfers still in progress at the exact closing time of 2.00 pm Australian Central Standard Time WILL NOT be accepted and you will not receive an automatic "successful submission" email.

For example: If a supplier has six files to upload into the tenders box and at the closing time, and only four have been uploaded, then the whole submission will be rejected.

- It is strongly recommended that if your file(s) are in excess of 10MB in total and/or you are transferring data from within a corporate network that you are able to do so without restriction. We suggest you speak with your network administrator or IT staff and advise them of the size of the files you intend to submit, to ensure that internal file size restrictions in your network or from your PC do not prevent you from uploading to the TenderLink servers. DO NOT leave your submission to the last minute. City of Darwin have no control over the closing of Tender Boxes. If you need assistance, please contact the person on the front cover of the tender before the closing time. As a guide, you should begin your file transfer at least 1 hour prior to the closing time.

Subject to any extension by the Principal of the Tender Closing Time, late Tenders will not be accepted.

# EXTENSION OF TIME

The Principal, at its absolute discretion, may extend the Tender Closing Time for the submission of Tenders.

  - HARD COPY, FACSIMILE AND EMAILTENDERS

## Hard copy, Facsimile and email submissions will not be accepted for the Tender.

## OPENING OF TENDERS

Tenders received will be opened at the office of the City of Darwin in Harry Chan Avenue, Darwin, immediately after the closing of tenders, at 2.00 pm Central Standard Time on the specified date, or at a time suitable to City of Darwin.

## INFORMAL TENDERS

Any tender that does not comply with the requirements of, or which contains provision not required by the Tender Document, may be rejected.

## TENDER VALIDITY PERIOD

Tenders shall remain valid for a period of 90 days.  If a tender is not formal or complete in accordance with the Special Conditions of Tendering the tender validity period shall commence from the date on which the tender is formalised or completed to the satisfaction of the Superintendent.

## ALTERNATIVE PROPOSALS

Tenders shall be submitted in accordance with the Tender Documents.  Alternatives will be considered if submitted in addition to a conforming tender.

## CUSTOMS DUTIES

The Tenderer shall allow for any customs duty and primage applicable to all imported materials, plant and equipment required in connection with the work under the contract.

## DISCREPANCIES, ERRORS AND OMISSIONS IN TENDER DOCUMENTS

Should the Tenderer find any discrepancy, error or omission in the Tender Documents he shall notify the Superintendent in writing thereof on or before the closing date for the tenders.

## ASSESSMENT OF TENDERS

The assessment of tenders may take into account but not be limited to the following:

- Completeness (basic contractual/commercial compliance)

- Conformity with specified requirements

- Quality of Proposed Work Plans

- Comparative evaluation based on achieving best value for money

- Tenderer's performance on past Contracts including references, compliance with time frames, quality of service, contractual relations/administration

- Tenderer's resources for executing works, including plant and equipment,

- Compliance with Occupational Health and Safety

Tenderers are advised that each of the selection criteria may not be given equal weight.  The objective of the assessment is to select the tender most advantageous to Council.

Tenderers may provide any relevant factors on the Declaration of Supporting Information clause 7.11 of the Form of Tender, addressing the selection criteria, that may assist the Council in making an assessment of the tender.

The Council supports development of local industry within the principle of value for money and, where appropriate, Tenderers should highlight the commercial, technical and economic benefits of the local content contained in their tender.  The NT Industry Search and Opportunities office provides a free of charge professional service to assist in locating sources of supply for products and services.

## QUALITY SYSTEMS

Council recognises the benefits in dealing with Contractors who have quality systems formulated in accordance with relevant Australian Standards.  Consequently, Tenderers with accreditation will, subject to other relevant criteria, be considered favourably against Tenderers who have no accreditation or those who do not intend to obtain accreditation.

## ACCEPTANCE OF TENDERS

Council shall not be bound to accept the lowest or any tender, however, Council reserves the right to accept a tender in whole or in part.

A Tender shall not be deemed to have been accepted unless and until notice in writing of such acceptance is handed to the Tenderer or is sent by prepaid post to or is left at the address stated in the Tender Form for the service of notice.

Unless a Formal Instrument of Agreement is executed, the Form of Tender, Conditions of Tendering, Special Conditions of Contract, General Conditions of Contract AS4000-1997, Annexure, and such Specifications, Schedules/Bill of Quantities Drawings and the tender documents as issued by the City of Darwin for the purpose of tendering together with the notice in writing of acceptance of the Tender shall constitute the Contract between the Principal and the successful Tenderer.

## INSURANCE

1.23.1	Property Damage and Public Risk

The Contractor shall be liable for and keep indemnified the Principal from and against any compensation paid or expense arising from any claim, demand, action, suit or proceeding that may be made or brought by any person against the Principal, the Superintendent or the employees, professional consultants or agents of the Principal or any claim that is not the fault of the Principal.

In connection with the carrying out of this Contract, The Contractor shall not be rendered liable for or in respect of personal injury to or the death of any person or loss of or damage to property resulting from any breach by the Principal of any provision of the Contract or any negligent act or omission of the Principal, the Superintendent or the employees, professional consultants or agents of the Principal or for or in respect of any claims, demands, actions, suits or proceedings, costs and expenses whatsoever in respect thereof or in relation thereto.

1.23.2	Public Liability Insurance

Before commencing work under the Contract, the Contractor shall take out a Public Liability Policy of Insurance.  The City of Darwin shall be noted on the policy as an interested party.

The Public Liability Policy of Insurance shall be for an amount not less than Twenty million dollars ($20,000,000.00) for any one occurrence and shall be effected with an insurer or insurers approved in writing by the Principal and in terms approved in writing by the Principal, which approvals shall not be unreasonably withheld.  The policy shall be maintained during the currency of the Contract.

1.23.3	Inspection and Provisions of Insurance Policies

Before commencing work under the Contract and whenever requested thereafter in writing at any time and from time to time thereafter so to do by the Principal, the Contractor shall produce evidence to the satisfaction and approval in writing of the Principal of the insurances effected and maintained by the Contractor and his sub-contractors.

1.23.4	Insurance of Employees

Before commencing work under the Contract, the Contractor shall ensure full compliance with the Work Health Act currently in effect in the Northern Territory.

1.23.5	Workers Compensation Insurance

For the purpose of this clause “worker” shall have the definition it is given in the “Work Health Act” as amended.

The Contractor shall maintain for the duration of the Contract appropriate Workers Compensation insurance cover for all workers employed by the Contractor.  This cover shall comply with the “Work Health Act” of the Northern Territory and policies shall be purchased from Northern Territory approved insurers.

The following information shall be provided with all tenders and as requested during the currency of the Contract:

- for contractors employing workers;

- workers compensation policy number;

- name of insurer and

- date of expiry.

The Contractor shall ensure that all sub-contractors who employ workers have Workers compensation insurance cover in accordance with the “Work Health Act” (1986) as amended.

The Contractor shall ensure that all persons employed under labour hire agreements, whether by the Contractor or through a Labour Hire Firm, are appropriately covered by Workers Compensation insurance.

Self-employed Contractors should ensure that they have adequate insurance coverage in place.

The Contractor shall be responsible for ensuring that all sub-contractors have appropriate insurance policies, and, upon request, shall provide to the Superintendents Representative copies of all insurance documents, including those of any sub-contractors (including self-employed contractors and person employed under Labour Hire Agreements).

## INTERPRETATION OF TERMS

‘Date of Acceptance’ means the date, which appears on the written notice, or Purchase Order issued by the Principal accepting the Tenderer's tender submission.

‘Lump Sum’ means the total sum which will have become payable to the Contractor by the Principle for the completion of the works

‘Person’ means a natural person, or a corporation, partnership, joint venture, incorporated association, government, local government authority or agency.

‘Purchase Order’ means an order issued to the Contractor by the Principal providing essential detail of a particular supply requirement.

‘Schedule of Rates' means any schedule included in the contract that shows the respective unit rate of payment for the supply of the Goods, and unless otherwise stated the unit rate shall be in Australian dollars and inclusive of GST.

‘the Authorised Officer’ is the person so named on an official Purchase Order.

‘the Contract’ means the document which constitutes or evidences the final and concluded agreement between the Principal and the Contractor concerning supply of the Goods.

‘the Contractor’ means the Person who as party to the Contract is bound to supply the Goods in accordance with the Contract and includes that Persons  heirs, executors, administrators and permitted assigns and in the case of a corporate body its successors and permitted assigns.

‘the Principal’ means the City of Darwin; the address of the Principal for the service of notices is Chief Executive Officer, City of Darwin, GPO Box 84, Darwin, NT 0801.

'the Superintendent' means the General Manager Infrastructure on behalf of the Principal.

‘the Specification’ means the detailed description of works, workmanship and materials to be carried out under this Contract.  It includes the description of items set out in the Schedule of Rates or the Purchase Order specifying the works.

‘Unit Price’ means the price per unit of the Goods stated in the Schedule of Prices or Purchase Order.

This Page Left Intentionally Blank

###### SECTION 2.00

SPECIAL CONDITIONS OF CONTRACT

SECTION 2.00       SPECIAL CONDITIONS OF CONTRACT

SECTION                SUBJECT

2.1			WORKING DAYS AND HOURS

2.2			NOTIFICATION

2.3			VEHICLE ACCESS

2.4			SITE AFTER HOURS

2.5			DUST

2.6			SAFETY REQUIREMENTS

2.7			ALTERNATIVE MEANS

2.8			VEHICLE DECAL

2.9			CONFIDENTIALITY

2.10			CLAIMS FOR PAYMENT

2.11			PAYMENT

2.12			GST AND OTHER EXPENSES TO BE INCLUDED IN RATES

2.13			PRICE VARIATION

2.14			CUSTOMER SERVICE

2.15 			SEPARABLE PORTIONS

# SPECIAL CONDITIONS OF CONTRACT

## WORKING DAYS AND HOURS

All work shall be scheduled to occur within Council’s ordinary hours wherever possible.  These are 8:00am – 4:15pm Monday to Friday, not including NT Public Holidays.  However, works are permitted to be spread across the following sets of hours:

- 7:00am to 5:00pm Monday to Friday

- 9:00am to 5:00pm Saturdays for all roads in residential areas where directed by the Contract or the Superintendent

- 7:00pm to 5:00am Monday to Friday where directed by the Contract or the Superintendent

- 7:00pm to 5:00am Sunday to Thursday for works in the Darwin CBD.

If the nature of the site requires work to be carried outside of the abovementioned hours, then this must be nominated on the program and approved in writing by the Superintendent.

## NOTIFICATION

The Contractor shall give the Superintendent not less than 24 hours’ notice for inspection of the Hold Points as described in the Technical Specification.

It is the Superintendent’s responsibility to inspect the work within that period and if for any reason unable to do so, to notify the Contractor and to grant an appropriate extension of time for completion.

Under no circumstances is the Contractor to proceed with the construction until each phase of the work has been inspected and approved by the Superintendent.

## PUBLIC NOTIFICATION

The Contractor shall be responsible for delivering notification to residents prepared by the City of Darwin at least one (1) week prior to the commencement of works.  The Contractor shall continually keep residents informed, including requests not to park vehicles on the road, by means of their own notification.

## SAFETY REQUIREMENTS

### Works and Materials

All works carried out under this Contract, including methods of construction, and use and storage of materials shall comply with relevant safety legislation and where no such legislation exists shall be made safe so as to protect persons and property.

### Protective Clothing and Safety Equipment

It is the Contractor’s responsibility to ensure that their employees and Subcontractors are suitably equipped and attired for the conditions under which they work.

Should unsuitably attired or equipped personnel be observed on site, the Superintendent may instruct suspension of works and/or removal of the offending persons from the site.

NOTE: The requirements of this clause are in addition to the Work Health Act and Work Health Regulations and do not release the Contractor from full compliance with all relative legislation.

### NT White Card

The NT White Card, or equivalent Worksafe approved construction card, is mandatory for all employees working onsite for this Contract as it forms the minimum acceptable requirements in meeting employer’s obligations under the Workplace Health and Safety Regulations.

## ALTERNATIVE MEANS

### The Principal may carry out any services of the same or a similar nature to the Services by any means without prior notice or justification to the Contractor.

The Contractor shall have no rights whatsoever under the Contract to make any claim arising out of any such services being carried out by the Principal.

## VEHICLE DECAL

The Contractor's business name, emblem and contact details, in conjunction with the specified Principal decal must be clearly displayed on all vehicles and significant plant and equipment required to carry out the Services as determined by the Superintendent.  See Section 8 attachment B.

- The specification for Principal decals is to be confirmed in writing by the  Superintendent

- The Contractor must pay all costs incurred in the production and fitting of the specified decal

- The Contractor must only display the decals for WUC and shall be magnetic in nature.  The decals shall not be displayed at any other times.

## CONFIDENTIALITY

Information collected under this Contract remains the property of the Principal.  The Contractor or its employees, agents, directors, partners, shareholders or consultants shall not disclose to any person, any information or documentation relating to the Principal of the affairs of others which may have come to its or their knowledge as a result of the Contract or performance of the Works and shall take all necessary precautions to prevent unauthorised access to such information or documentation.

The Contractor shall not divulge any information regarding the nature of progress of the Works or give any publicity concerning the Works except with the written consent of the Principal.

## CLAIMS FOR PAYMENT

The Contractor shall submit claim for payment, at intervals of not less than one month to be received by the Principal by the seventh (7) day of the following month.  The claim for payment in the form of a detailed invoice relating to each individual job and shall cover the whole of the job.

All invoices submitted must adhere strictly to the Schedule of Rates. Incorrect invoices will not be accepted and will be returned to the Contractor.  Payment will be made 30 days after the end of the month in which a correct invoice is raised.

For additional works outside the contract, a purchase order must be obtained from the Superintendent’s Representative and the invoice must refer to the purchase order number.

The invoice shall comply with the requirements of the GST Law (as a Tax Invoice) and shall, unless inconsistent with the GST Law, specify the following:

Each invoice shall detail:

(a)	the Principal’s Purchase Order Number;

(b)	the specific Schedule of Rates item no. for the particular works including description (item name);

(c)	the specific Quantity of the item no;

(d)	the specific Rate of the item no; and

(e)	the extended total of each specific item no. (multiplying rate x item no.)

(f)	the amount of any GST  paid or payable by the Contractor with respect to the Fees;

(g)	the date of delivery of the Services to which the invoice relates;

(h) 	the Contractor’s address for payment.

(i)	Local Industry Participation Plan (LIPP) report

(k)	Spray sheets and actual spread rate results (see clause 6.5.7) for spray seals and/or asphalt quality documentation

All invoices shall be submitted by post to City of Darwin GPO Box 84 Darwin 0801 or emailed to accounts payable accountspayable@darwin.nt.gov.au

The Principal will process detailed invoices received at the Principals address by the thirtieth (30) day of the following month.

(ie.  Work performed in September should be invoiced dated September and received by Council on or before the seventh (7) October, to be processed for payment by thirtieth (30) October).

The Principal reserves the option to not process detailed invoices received after the seventh (7) day of the following month until the next month.

(ie. using the above example, if invoice received after the 7th of September, payment would be made 30 November).

## PAYMENT

On receipt of a claim for payment in accordance with clause 2.11 the City of Darwin will transfer funds electronically or mail cheque payments as required under the General Conditions of Contract.

In cases where hourly rates apply, a statement of man-hours shall be in the form of a daily time sheet for each employee and shall include:

- Job details – location and a brief description of work carried out.

- The name of the employee.

- The actual times of start and finish.

- The details of materials used and any approved plant hire.

The Council reserves the right to deduct from any payment to the Contractor any monies payable by the Contractor to the Council.

## GST AND OTHER EXPENSES TO BE INCLUDED IN RATES

The Tendered Rates, inclusive of all expenses of the Contract, insurance, duties, imposts and taxes which shall be paid by the Contractor, are inclusive of GST.

## PRICE VARIATION

The Contractor may apply for a variation in rates on the anniversary of the contract in each year. The application must be submitted no later than four weeks after the anniversary date, and shall be in writing and supported by evidence on which the claim is based.

The rates to be negotiated shall have regard but not be limited to:

(a) 	The percentage change in the All Groups Consumer Price Index for the City of Darwin as published by the Australian Bureau of Statistics between the end of the quarter immediately preceding the commencement of the Term or the last Review Date, whichever is the later, and the end of the quarter immediately preceding the Review Date.

(b)  Changes in Government taxes.

## CUSTOMER SERVICE

A positive commitment to Customer Service shall be demonstrated by the Contractor and Sub-Contractors, towards Council's clients and ratepayers. The Contractor's employees shall at all times be polite and courteous to all members of the public, and not engage in contentious discussion or behaviour.

## SEPARABLE PORTIONS (SECTION 9 – ANNEXURE PART A)

The works shall be performed as per the Separable Portions detailed in Section 9 – Annexure Part A and are subject to separate commencement dates, practical completion dates and liquidated damages.

###### SECTION 3.00

GENERAL CONDITIONS OF CONTRACT

SECTION 3.00		GENERAL CONDITIONS OF CONTRACT

SECTION		SUBJECT

  - GENERAL CONDITIONS

  - INFORMATION PRIVACY ACT

# GENERAL CONDITIONS OF CONTRACT

## GENERAL CONDITIONS

The General Conditions of Contract governing this Contract are AS4000 – 1997 General Conditions of Contract.

## INFORMATION PRIVACY ACT

In this clause:

Act means the Information Act (NT)

Privacy Laws means the Act; and the Information Privacy Principles set out in the Act or any ‘code of practice’ approved under the Act that applies to any of the parties to this Contract.

Personal Information means all information about a person that is “personal information” as defined in the Act which is collected and/or handled by any of the parties in connection with this Contract.

- The Contractor agrees to deal with all Personal Information in a manner which is consistent with the Privacy Laws and any other relevant privacy legislation, as if the Contractor were a public sector organisation.

- The Contractor is to collect, use, disclose or otherwise deal with Personal Information only for the purposes of fulfilling its obligations under this contract.

- The Contractor is not to disclose Personal Information without the written authority of the Council, and in any event disclosure is to be in accordance with the Privacy Laws.

- The Contractor is to immediately notify the Council where it becomes aware that a disclosure of Personal Information may be required by law.

- The Contractor is to ensure that any employees, agents or subcontractors, and any other person who may have access to Personal Information held by the Contractor, are aware of the obligations of the Contractor under this agreement and undertake to not collect, access, use, disclose or otherwise deal with Personal Information except in performing their duties of employment and in accordance with this agreement.

- The Contractor is to take all reasonable measures to ensure that Personal Information is protected from misuse and loss and from unauthorised access, modification, disclosure or other misuse and that only personnel necessary to fulfil the obligations under this agreement have access to the Personal Information.

- The Contractor is to develop, and obtain the written approval of the Council,:

- policies for the management of personal information; and

- complaint handling procedures.

Each party is to immediately notify the other when a complaint is received.

- The Contractor acknowledges that individuals have the right to request access to, or correction of, the Personal Information held about them.

- The Contractor must not transfer Personal Information outside the Northern Territory without the prior approval of the Council.

- The Contractor, in respect to Personal Information, is to immediately notify the Council where the Contractor becomes aware of a breach of this clause or the Privacy Laws.

- The Contractor indemnifies the Council in respect of any liability, loss or expense incurred arising out of or in connection with a breach of the obligations of the Contractor under this agreement.

- When this agreement expires or is terminated, the Contractor must, at the Council's discretion:

- either return to the Council all records containing Personal information;

- retain any material containing Personal Information in a secure manner as approved by the Council; or

- destroy or delete any Personal Information.

This sub-clause will survive the expiration or termination of this Contract.

- The Contractor shall indemnify the Council and keep the Council indemnified against any failure of the Contractor to comply with its obligations under this clause.

###### SECTION 4.00

ANNEXURE

# PART A	ANNEXURE A TO AS4000 – 1997 General Conditions of Contract

| 1 | Principal | City of Darwin |
| --- | --- | --- |
| 2 | Principal address | GPO Box 84 Darwin, NT 0801 Civic Centre, Harry Chan Avenue, Darwin, NT 0800 |
| 3 | Contractor |  |
| 4 | Contractors Address |  |
| 5 | Superintendent | General Manager – Engineering & City Services City of Darwin |
| 6 | Superintendent’s Address | GPO Box 84, Darwin, NT 0801 Civic Centre, Harry Chan Avenue, Darwin, NT 0800 |
| 7 a) b) c) d) | Date for Practical Completion Or Period of time for Practical completion Time for commencement from date of acceptance of tender: Time for completion from date of acceptance of Tender | Refer to Clause 5.2 Construction Program for specific dates |
| 8 | Governing Law | Northern Territory |
| 9 a) b) c) | Currency Place for payments Place of Business of Bank | Australian Dollars Darwin NT Darwin NT |
| 10 a) b) c) | Bills of Quantities Alternative applying If alternative applies, is the bill of quantities to be priced? Lodgement time | Not Applicable No |
| 11 | Quantities in Schedule of Rates, limits of accuracy | 85-125% (Separable Portions 1 – 3) N / A (Separable Portion 4) |
| 12 | Provisional Sum, Percentage for profit and attendance | Not Applicable |
| 13 a) b) c) d) e) | Contractors security Form Amount Retention moneys Time for provision (except for retention monies) Additional security for unfixed plant and materials | Unconditional Bank Guarantee 2 x 2.5% of the Contract Sum Not Applicable Prior to issue of Possession of Site Certificate Not applicable |
| 14 | Principal’s security | Not applicable |
| 15 | Principal supplied documents | 2 copies |
| 16 | Time for Superintendent’s direction about documents | 7 days |
| 17 | Subcontract work requiring approval | Not Applicable |
| 18 | Novation |  |
| 19 a) b) | Legislative requirements Those excepted Identified WUC | Nil All WUC |
| 20 a) b) c) d) e) | Insurance of the Works Alternative applying If alternative 1 applies, Provision for demolition and removal of debris Provision for consultants’ fees Value of materials or things to be supplied by the Principal Additional amount or percentage | Alternative 1 Nil Nil Nil Nil |
| 21 a) b) | Public Liability Insurance Alternative applying If alternative 1 applies Amount per occurrence shall not be less than | Alternative applying $20,000,000.00 (twenty million dollars) with City of Darwin noted as an interested party thereon |
| 22 | Time for giving possession | 7 days - On receipt of items 13 and 21 of this annexure |
| 23 a) b) | Qualifying causes of delay Causes of delay for which EOTs will not be granted | Not applicable Not applicable |
| 24 | Liquidated damages rate (per day) | Not Applicable |
| 25 a) b) | Bonus for early practical completion Rate Limit | Not applicable |
| 26 | Delay damages, other compensable causes | Nil |
| 27 | Defects Liability Period | 52 weeks from Practical Completion of each Separable Portion or Work Order |
| 28 a) b) | Progress Claims Times of progress claims Stage of WUC for progress claims | Every 28 days from commencement to Practical Completion of each year’s program |
| 29 | Unfixed plant and materials for which payment claims may be made | Nil |
| 30 | Interest on overdue payments | Nil |
| 31 | Time for Principal to rectify inadequate possession | 7 days |
| 32 | Arbitration | President of the Institute of Arbitrators & Mediators Australia |

PART B	ANNEXURE TO AS4000 – 1997 General Conditions of Contract

DELETIONS

The following clauses have been deleted from the general conditions in AS4000-1997: Clauses 8.5 and 8.6.

AMENDMENTS

The following clauses have been amended and differ from the corresponding clauses in AS4000-1997:

Clause 7 is entirely replaced with the following:

“7.   	Service of Notices

All notices and other documents which must or may be served under this Contract may be served in the following manner:

(a)	On the Principal by hand delivery to its street address shown in the Part A annexure or be email to the address shown in the Part A annexure.

(b)	If the Contractor is a natural person, by personal service or by hand delivery to the address shown in the Part A annexure or by email to the address shown in the Part A annexure.

(c)	If the Contractor is a corporation, then in accordance with the Corporations Act or by email to the address shown in the Part A annexure.”

Clause 16 is entirely replaced with the following:

“16.   	Insurance of the Works

The Contractor shall throughout the term of the contract maintain the following insurances with a reputable insurer:

(a)	In respect of all the Contractor’s plant and equipment used in the WUC, for their market or full replacement value as specified in the insurance certificate;

(b)	In respect of all materials supplied or to be supplied by the Contractor as part of the Works, against usual risks, for their full replacement value.”

Clause 25 is entirely replaced with the following:

“25.   	Latent Conditions

25.1 	Asbestos

Asbestos accumulations may exist on the site of the works.  If asbestos is discovered during the works, all works must cease until an appropriate Asbestos Management Plan is in place.  The Contractor shall be responsible for costs related to the development and implementation of the Asbestos Management Plan.

Clause 31 is entirely replaced with the following:

“31.	Working Hours

All WUC shall be scheduled to occur within Council’s ordinary hours wherever possible.  These are 8:00am – 4:15pm Monday to Friday, not including NT Public Holidays.  However, works are permitted to be spread across the following sets of hours:

- 7:00am to 5:00pm Monday to Friday

- 9:00am to 5:00pm Saturdays for all roads in residential areas where directed by the Contract or the Superintendent

- 7:00pm to 5:00am Monday to Friday where directed by the Contract or the Superintendent

- 7:00pm to 5:00am Sunday to Thursday for works in the Darwin CBD.

If the nature of the site requires work to be carried outside of the abovementioned hours, then this must be nominated on the program and approved in writing by the Superintendent.

Clause 32 is entirely replaced with the following:

“32.	Programming

(a)	The program of works as completed by the Contractor during the tender process, in accordance with the program requirements listed in each of the Separable portions, and as subsequently amended from time to time with the written consent of the Superintendent, forms part of this Contract.

(b)	The Contractor shall provide an up to date program of works at least fortnightly, or within two business days of being requested, to take account of actual progress of the WUC and any anticipated effect on future progress of the WUC.”

Clause 34.3 is amended by the reference to “28 days” becoming “14 days.”

Clause 34.5 is amended by “28 days” becoming “7 days.”

Clause 37 is entirely replaced with the following:

“37.	Payment

37.1.  	Progress Claim

The Contractor shall submit claim for payment, at intervals of not less than one month to be received by the Principal by the seventh (7) day of the following month.  The claim for payment in the form of a detailed invoice relating to each individual job and shall cover the whole of the job.

All invoices submitted must adhere strictly to the Schedule of Rates. Incorrect invoices will not be accepted and will be returned to the Contractor.  Payment will be made 30 days after the end of the month in which a correct invoice is raised.

For additional works outside the contract, a purchase order must be obtained from the Superintendent’s Representative and the invoice must refer to the purchase order number.

The invoice shall comply with the requirements of the GST Law (as a Tax Invoice) and shall, specify the following:

(a)	the Principal’s Purchase Order Number;

(b)	the specific Schedule of Rates item no. for the particular works including description (item name);

(c)	the specific Quantity of the item no;

(d)	the specific Rate of the item no; and

(e)	the extended total of each specific item no. (multiplying rate x item no.)

(f)	the date of delivery of the Services to which the invoice relates;

(g) 	the Contractor’s address for payment.

(h)	Local Industry Participation Plan (LIPP) report

(i)	Spray sheets for spray seals and/or asphalt quality documentation

All invoices shall be submitted by post to City of Darwin GPO Box 84 Darwin 0801 or emailed accountspayable@darwin.nt.gov.au

Clause 37.2 is amended by deleting the penultimate paragraph and replacing it with the following:

37.2 	Handling of Progress Claims

The Principal will process detailed invoices received at the Principals address by the thirtieth (30) day of the following month.

(ie. Work performed in September should be invoiced dated September and received by Council on or before the seventh (7) October, to be processed for payment by thirtieth (30) October).

The Principal reserves the option to not process detailed invoices received after the seventh (7) day of the following month until the next month.   (ie. using the above example, if invoice received after the 7th of September, payment would be made 30 November).

37.4	Final payment claim and certificate

Within 28 days after the expiry of the last defects liability period, the Contractor shall give the Superintendent a written final payment claim endorsed ‘Final Payment Claim’ being a progress claim together with all other claims whatsoever in connection with the subject matter of the Contractor.

Within 42 days after the expiry of the last defects liability period, the Superintendent shall issue to both the Contractor and the Principal a final certificate evidencing the moneys finally due and payable between the Contractor and the Principal on any account whatsoever in connection with the subject matter of the Contract.

Those moneys certified as due and payable shall be paid by the Principal or the Contractor, as the case may be, within 7 days after the debtor receives the final certificate.

The final certificate shall be conclusive evidence of accord and satisfaction, and in discharge of each party’s obligations in connection with the subject matter of the Contract except for:

(a) 	Fraud or dishonesty relating to WUC or any part thereof or to any matter dealt with in the final certificates;

(b) 	Any defect or omission in the Works or any part thereof which was not apparent at the end of the last defects liability period, or which would not have been disclosed upon reasonable inspection at the time of the issue of the final certificate;

(c) 	Any accidental or erroneous inclusion or exclusion of any work or figures in any computation or an arithmetical error in any computation; and

(d) 	Unresolved issues the subject of any notice of dispute pursuant to clause 42, served before the 7th day after the issue of the final certificate.

Clause 39.2 is amended by deleting the words “by hand or by certified post” which appear in the second line of that subclause.

Clause 39.7 is amended by deleting the words “by hand or by certified post” which appear in the second line of that subclause.

ADDITIONS

The following clauses have been added to those of AS4000-1997:

44 	Specifications

The Technical Specifications and works program annexed form part of the Contract.  The WUC shall be carried out in accordance with those Technical Specification and program or as they are amended from time to time by the Superintendent.

45	Work Health and Safety

The Contractor shall at all times comply with its obligations under the Work Health and Safety National Uniform Legislation Act and is deemed to be the Principal Contractor for the purposes of that Act.   The Contractor shall ensure that all its employees hold a White Card or otherwise comply with the Northern Territory Code of Practice for Induction for Construction Work.

46	Vehicle Decal

The Principal’s decal must be clearly displayed on all vehicles and significant plant and equipment used to carry out the works under Contract and shall be removed at all other times.

47. 	Confidentiality

Information collected under this Contract remains the property of the Principal.  The Contractor or its employees, agents, directors, partners, shareholders or consultants shall not disclose to any person, any information or documentation relating to the Principal of the affairs of others which may have come to its or their knowledge as a result of the Contract or performance of the Works and shall take all necessary precautions to prevent unauthorised access to such information or documentation.  The Contractor shall not divulge any information regarding the nature of progress of the Works or give any publicity concerning the Works except with the written consent of the Principal.

48.	GST

The contract sum is inclusive of GST.

49.	Australian Standards

Where any of the materials supplied by the Contractor for the purposes of the WUC, or where any aspect of the WUC is subject to an Australian Standard, the Contractor shall comply with that applicable Australian Standard.

PART C - ATTACHMENTS to this Tender Document

- Attachments that will form part of the contract

2019-058 	Schedule of Rates

2019-058	Locality and Area Plans for Project Works

2019-058 	Tender Return Forms

2019-058 	Technical Specification

2019-058 	Program of Works

- Attachments that provide supporting information to tenderers.

2019-058 Supporting Information

Separable Portions Tables of Streets to be treated

Northern Territory Government 2017 Standard Specification for roadworks

Traffic Signal Detector Loop Reinstatement detail.

This Page Left Intentionally Blank

###### SECTION 5.00

PRELIMINARY CLAUSES

SECTION 5.00       	 PRELIMINARY CLAUSES

SECTION                	SUBJECT

5.1			DESCRIPTION OF THE WORKS

5.2			CONSTRUCTION PROGRAM

5.3			SITE INFORMATION

5.4			EXISTING STRUCTURES AND SERVICES

5.5			SITE AMENITIES

5.6			MEASUREMENT OF WORK

5.7			SURVEYS AND SETTING OUT

5.8			SCHEDULE OF DRAWINGS

5.9			COMPLIANCE WITH STANDARDS AND CODES

5.10			PUBLIC RELATIONS

5.11			BY-LAWS, FEES AND NOTICES

5.12			JOINING UP

5.13			DAMAGE TO SERVICES

5.14			DAMAGE TO VEHICLES AND / OR PROPERTIES

5.15			LIGHT AND POWER

5.16			WATER

5.17			SITE MEETINGS

5.18			ENVIRONMENTAL PROTECTION

5.19			LOADING AND SIZE OF VEHICLE

5.20			OBVIOUS WORKS

5.21			CYCLONE PRECAUTIONS

# PRELIMINARY CLAUSES

  - DESCRIPTION OF THE WORKS

The work comprises the supply of all labour, plant and materials necessary for the hot-mixed asphalt and sprayed bitumen works on various roads and other areas within the Municipality of Darwin the 2019/20 financial year, in accordance with the accompanying Conditions of Contract, to the complete satisfaction of the Superintendent.  The works are for:

- Specific project sites as identified in this document

- Periodic supply and placement of asphalt and spray seals as directed by the Superintendent

The work also includes the reinstatement of all existing line marking and Raised Reflective Pavement Markers (RRPM) on pavement damaged and/or removed by the resealing and/or overlaying work and the installation of new Raised Reflective Pavement Markers as per AS 1742.2 on these pavements.

The Superintendent may add to, or delete any parts of the works, giving one weeks’ notice to the Contractor.

NOTE: When the works carried out in the city or in a high profile area, may cause inconvenience to adjacent residents, businesses and general road users, the contractor shall carry out the works in a manner that minimises inconvenience and disruption to services and adjacent residences.

Particular attention shall be paid to control of dust, noise and fumes.  Property access for business and emergency must be maintained whenever possible.  The Contractor must accommodate emergency vehicles as required.

Traffic control and pedestrian safety must be given the highest priority.  Liaison and communication with public and stakeholders is critical.  Work Safe NT may monitor the project closely.

  - CONSTRUCTION PROGRAM

The works will be guided by the following dates;

| Milestone | Construction Hours | Commencement Date | Practical Completion Date |
| --- | --- | --- | --- |
| SEPARABLE PORTION 1 Cavenagh Street (Stage 1) | Night | On award of tender | 27 September 2019 |
| SEPARABLE PORTION 2 Daly Street & Cavenagh Street (Stage 2) | Night | 2 March 2020 (or as directed by Superintendent) | 29 May 2020 |
| SEPARABLE PORTION 3 Periodic Works | As directed by Superintendent | As directed by Superintendent | As directed by Superintendent |

Works Program

- The contractor shall have the flexibility to prepare their work program to suit the possibility of wet weather conditions

- The works program must be continuous and uninterrupted for the duration of the separable portions

- All committed works with others must be taken into consideration when preparing the program

- The program shall be in the form of a bar graph, or Gantt chart

- The program shall list each road and the anticipated time spent, in days

- The program must ensure works reach Practical Completion by the Milestone Date for each Separable Portion and include allowances for minor delays, such as weather

During the course of the contract if the weather forces some changes to the program the contractor shall inform the Superintendent immediately and provide an amended program within 2 days.

  - SITE INFORMATION

The Superintendent does not represent that information made available shows completely, the existing site or sub-surface conditions. The Tenderer shall make his own interpretations, deductions and conclusions from the information made available and shall accept full responsibility for such interpretations, deductions or conclusions.

  - EXISTING STRUCTURES AND SERVICES

Any connections, disconnections or interference with existing structures and services shall be carried out under the supervision of the Superintendent to whom reasonable notice shall be given by the Contractor of his intention.

  - SITE AMENITIES

The Contractor shall provide all statutory and necessary amenities and sanitary facilities for workmen and other persons lawfully upon the site and remove them on completion of the works.

  - MEASUREMENT OF WORK

Unless other specified, all measurements of work for the Contract shall be in accordance with Australian Standard Method of Building Works as authorised by agreement between the Master Builders’ Federation of Australia and the Australian Institute of Quantity Surveyors, or, in the case of civil engineering work, with Australian Standard AS1181 Method of Measurement of Civil Engineering Quantities.

  - SURVEYS AND SETTING OUT

Council supervisor will indicate the exact limits of work on site to the Contractor.

  - SCHEDULE OF DRAWINGS

This contract has no drawing.

  - COMPLIANCE WITH STANDARDS AND CODES

Where the Contract requires the Contractor to comply with any standard or code, that standard or code shall, unless otherwise specified, be that which is current at the closing date for tenders.

If, subsequent to the award of the Contract, any such standard or code is amended, the Superintendent may direct that the Contractor to comply with such amendments and the cost to the Contractor of such compliance will be dealt with under the General Conditions of Contract.

  - PUBLIC RELATIONS

    - Before Carrying Out Works

The Contractor shall draft a letter in consultation with Council.  The Contractor shall carry out letterbox drops to all affected residents two days prior to carrying out the various sections of work and any other event which may cause disruption and inconvenience.

The Contractor must provide proof of carrying out the letterbox drops.

    - During Carrying Out Works

The Contractor staff shall be courteous to the public at all times in matters relating to this Contract including but not limited to traffic control, spraying and sweeping etc.

    - After Carrying Out Works

Before the end of the defect liability period, the Contractor shall attend promptly and resolve satisfactorily all complaints from the public, relating to the works under this Contract.

  - BY-LAWS, FEES AND NOTICES

Unless otherwise specified, the Contractor is responsible for connection of all water, drainage, sewerage, gas and electricity services and he shall apply for all relevant permits and pay all associated fees and/or charges which are levied by the appropriate Authorities.

  - JOINING UP

Where the method of joining up of work is not otherwise specified, the joining of all old and new work and the cutting away for connections shall be carried out in a manner approved by the Superintendent and made good in all trades to match existing adjacent work.

  - DAMAGE TO SERVICES

It shall be the duty of the Contractor to ascertain the true location of all services, whether these services are shown on the contract documents or not, and it shall be the responsibility of the Contractor to make good and restore to the satisfaction of the relevant authority, any damage caused by the Contractor or his Sub-Contractor during execution of the works.

  - DAMAGE TO VEHICLES AND / OR PROPERTIES

The Contractor shall be responsible for any damage to vehicles and/or properties affected by the work under this contract.

  - LIGHT AND POWER

The Contractor shall be responsible for all costs and charges and the installation of any temporary electric light and power installation required, all in accordance with appropriate regulations.

  - WATER

The Contractor shall arrange for the supply of all water required for executing the works under the Contract and pay all incidental charges, including the cost of water used.

  - SITE MEETINGS

The Contractor shall arrange conferences as required by the Superintendent between himself and the Superintendent and consultants and appropriate subcontractors throughout the duration of the Contract. The Contractor shall keep minutes of such meetings and have two copies thereof forwarded to the Superintendent as soon as possible after each meeting.

At the first site meeting the Contractor shall submit to the Superintendent the names and telephone numbers of all responsible persons who may be contacted for after-hours calls during the course of the contract.

  - ENVIRONMENTAL PROTECTION

    - Site Control

The Contractor and all Sub-Contractors shall observe all rules and regulations in force on the site and shall comply with all notices and instructions issued by the Superintendent in relation to such rules and regulations.

Except as otherwise provided in the Contract, delivery of materials for the works, space for storage of same and for building sheds, office and workshops will be allowed only as arranged between the Contractor and the Superintendent.

Flammable or combustible materials are to be stored or used strictly in accordance with any instructions given by the Superintendent concerning their storage and use.

All materials and equipment on site shall be stored in such a manner as to prevent mechanical and climatic damage.  Storage areas shall be kept in a neat and tidy manner to minimise hazards to persons, materials and equipment.

    - Environmental Control

The Contractor shall be responsible for ensuring that the provision of this clause and any other environmental protection provisions in the Contract are complied with and that the requirements of any statute, by-law, standard and the like are observed.

The Contractor shall submit to the Superintendent his proposal for traffic movement, temporary structures (including lamps) cleaning up (including burning off) erosion control, demolition and the like.

After the proposals have been agreed to by the Superintendent, the Contractor shall be responsible for ensuring that the agreed proposals are observed.

Any changes in the agreed proposals shall be requested by the Contractor, and be subject to the agreement of the Superintendent.

    - Trucking

All trucks entering or leaving the site with loose materials or debris shall be loaded in a manner that will prevent dropping of materials on streets and shall have suitable tarpaulins fastened over the load before leaving the site.

The Contractor shall ensure that the wheels, tracks and body surface of all vehicles and plant leaving the site are free of mud and that mud is not carried onto adjacent paved streets or other areas.

    - Dust, Dirt and Water

Adjoining owners, residents and the public are to be protected against dust, dirt and water nuisance.  Dust screens and watering shall be used to reduce dust nuisance.

    - Preservation of Flora

The Contractor shall refrain from destroying, removing or clearing trees and shrubs to an extent greater than is necessary for execution of work under the Contract.

All areas to be cleared shall be inspected by the Contractor and the Superintendent’s approval obtained before any trees or shrubs are removed, cleared or destroyed.

  - LOADING AND SIZE OF VEHICLE

The Tenderer’s attention is directed to the Northern Territory Control of Roads Act 1953 – 1983 and amendments which prescribe limits on axle and wheel loads and on size of vehicles using public roads.

Any vehicle used by the Contractor for carting or similar operations on existing Northern Territory roads in connection with the work covered by this Specification shall comply with the conditions of the aforesaid Act.

  - OBVIOUS WORKS

If the specification doesn’t contain any mention of methods or parts, which in the opinion of the Principal are reasonable and obviously necessary for the satisfactory completion of the works, such methods or parts are to be provided by the Contractor without any extra charge as if they were specially mentioned and shall be deemed to be, and hereby are included in this Contract.

  - CYCLONE AND STRONG WIND PRECAUTIONS

During the period of 1st November to 30th April, and during periods of strong winds, the Contractor shall ensure that unfinished work, equipment, sheds, hoardings, materials and any other moveable items on the site are protected, stored or secured to the extent necessary to ensure that in strong wind conditions they will not be a danger to persons or property because of collapse, movement or any other cause.

This Page Left Intentionally Blank

###### SECTION 6.00

TECHNICAL SPECIFICATION

STANDARD TECHNICAL CLAUSES

Australian Standards, published by the Standards Association of Australia, are referred to throughout the specification and are part of the specification except where conflict arises, in which case this specification applies.  Australian Standards are identified by their reference number only.  Use the current Standards for this Contract.

Words in the singular include the plural and words in the plural include the singular according to the requirements of the context.

Words importing the masculine gender include the feminine gender or the neuter gender as the case may require.

The text of specifications as applicable to the works is quoted herein in full.  The presence of an asterisk before a clause (sub-clause) number in the index or in the text of the Tender Documents indicates that the clause (sub-clause) has been modified from that contained in the Standard Specification or is a new clause.

Numbering of clauses (sub-clauses) in the Tender Documents is not necessarily sequential and gaps in the sequence indicate that a clause (sub-clause) of the Standard Specification has been omitted from the requirements for the works.

Unless otherwise specified, this Contract utilises the Northern Territory Government’s 2017 Standard Specification for Roadworks.  Any specific requirements of the Principal detailed in this section shall override the Standard Specification used for this Contract.

Reference to “NT Government”, Northern Territory Government”, “NTG” and “DOI” shall be deemed to be interpreted as referring to the “City of Darwin”.

SECTION 6.00         TECHNICAL SPECIFICATION

SECTION                 SUBJECT

6.1   			MISCELLANEOUS PROVISIONS

6.2   			PROVISION FOR TRAFFIC

6.3 			SPRAY SEALING

6.4			DENSE GRADED ASPHALT

6.5			COLD MILLING PROFILE WORKS

6.6			CONFORMANCE TESTING

6.7			MEASUREMENT AND PAYMENT

- TECHNICAL SPECIFICATION

  - Miscellaneous Provisions

The Contractor shall refer to the Northern Territory Government Standard Specification for Roadworks “1. MISCELLANEOUS PROVISIONS” along with the following requirements which override any related provisions to the said specification:

6.1.1	The Contractor must complete an ITP prior to and during of each discrete segment of the works. See Section 8 Attachment C.

PROVISION FOR TRAFFIC

The Contractor shall refer to the Northern Territory Government Standard Specification for Roadworks “2. PROVISION FOR TRAFFIC” along with the following requirements which override any related provisions to the said specification:

## The Contractor shall provide an overarching Traffic Management Plan (TMP) for the Contract in accordance with Section 2.5 of the Specification.  This shall be submitted to the Superintendent for review and advice on suitability no later than 10 business days after the award of tender and shall be a HOLD POINT to this Contract.

Site specific TMPs and Traffic Control Diagrams (TCDs), which shall be attachments to the overarching TMP, shall be designed by a person qualified in Work Zone Traffic Management Level 1 Accreditation for each individual work site.  The person shall physically visit each site with proof of a detailed risk assessment which shall be included with the site specific TMP.  A separate TCD shall be included detailing signage for each site outside of working hours.

These site specific TMPs and TCDs shall be submitted for review by the Superintendent no later than five (5) business days prior to the commencement of works at the subject project site and is a HOLD POINT to this Contract.

## Generic Traffic Control Diagrams (TCDs) may be used for cul-de-sacs and local roads if supported by the detailed risk assessment for each project site and deemed suitable for use by the Superintendent.  Otherwise site specific TCDs shall be developed.

Site specific TCDs shall be developed for works on secondary and primary collector roads and sub-arterial and arterial roads.

Where traffic management devices and / or lane closures are required on Northern Territory Government (NTG) roads in order to facilitate the resurfacing works, the Contractor shall also obtain approval from the NTG and provide a copy of this approval to the Superintendent no later than five (5) business days prior to commencement of works at the site and is a HOLD POINT to this Contract.

6.2.2	Electronic Variable Message Signs (VMS) shall be used on sub-arterial and collector roads, or where directed by the Superintendent, and shall be displayed at least seven (7) calendar days prior to commencement of works.  As a minimum, there shall be one sign displayed on each approach to the project site.  The Contractor shall submit the proposed wording for review and approval by the Superintendent prior to the placement of the VMS and is a HOLD POINT to this Contract.  Messages shall be limited to a maximum of three (3) display screens.

6.2.3	Payment for the Provision for Traffic shall be:

- On a lump sum basis for the specific projects identified in Separable Portions 1 to 3 (inclusive).

- On the basis of the resources used as shown on the TCD and for the duration of the work at the location of each specific work order for Separable Portion 4.

  - SITE PREPARATION WORKS

6.3.1	The Contractor shall be responsible for the preparation of the site which may include the trimming of overhanging vegetation to allow for the resurfacing process.  The Contractor shall coordinate these works such that the clearing activities only take place once prior to the works.  A suitably qualified vegetation contractor shall be engaged to undertake this work.  Costs for the clearance of vegetation shall be borne by the Contractor and be deemed to be included in the Contract rates.

The Contractor shall advise the Superintendent of vegetation clearing requirements, if any, a least ten (10) business days prior to the commencement of works at each site and is a WITNESS POINT to this Contract.

6.4	CONFORMANCE TESTING

6.4.1	All conformance testing, including frequencies of testing, shall be undertaken in accordance with the requirements of the following Northern Territory Government Standard Specification for Roadworks:

- 5.	CONFORMANCE TESTING

- 8.	SPRAY SEALING

- 9.	DENSE GRADED ASPHALT (including both material and construction compliance testing)

- 15.	PAVEMENT MARKINGS

- 18.	TRAFFIC CONTROL SIGNALS AND INTELLIGENT TRANSPORT SYSTEMS

- Any other requirements listed in this Technical Specification

All costs related to the conformance testing of the requirements of the Contract shall be borne by the Contractor and deemed to be included in the Contract rates.

6.5	SPRAY SEALING

The Contractor shall refer to the Northern Territory Government Standard Specification for Roadworks “8. SPRAY SEALING” along with the following requirements which override any related provisions to the said specification:

## 6.5.1	The Contractor shall undertake a seal design to determine the binder spray rate and aggregate spread rates for each specific project site in accordance with Austroads AP-T68/06 Update of the Austroads Sprayed Seal Design Method.

The Contract’s seal design shall be undertaken by a Seal Designer who is a competent, trained person that has successfully attained the Australian Asphalt Pavement Association (AAPA) Statement of Attainment (prior to 2008 Certification of Attainment) for the course titled Sprayed Sealing Selection and Design.  The Contractor shall, as part of their tender submission, include a copy of this Statement of Attainment and evidence that they are listed on the current AAPA Spray Seal Design Course Registry.  Otherwise, the Contractor shall submit evidence that this qualification can be attained within two (2) calendar months of the award of tender.  This is a HOLD POINT to this Contract.

Prior to undertaking any seal design, the Seal Designer shall inspect each site in order to identify site-specific conditions for inclusion in design

## The Contractor’s seal design shall be submitted for each project site in the form of a report to the Superintendent for review for suitability at least five (5) business days prior to the commencement of works at each project site and is a HOLD POINT to the Contract.  The report shall include, but not be limited to, the following:

## Photos from the subject site.

## Traffic data, that is, AADT and heavy vehicle percentage, based in data supplied by the Principal.

## Test results for seal design inputs, including, but not limited to, a quarry certificate for aggregates and results from the sand patch testing in accordance with Austroads Test Method Q705 Texture Depth (Sand Patch).

- Binder Type.

- Cover aggregate nominal size and Average Least Dimension (ALD).

- Homogeneity of sections of carriageway impacting on design in accordance with the design procedure.

- Underlying pavement type on which the sprayed bituminous surfacing is to be applied

- Test results, assumptions, inputs, the design method and calculations that were used to determine the designed spray and spread rates.

- Documentary evidence of the Seal Designer’s successful attainment of the Australian Asphalt Pavement Association (AAPA) Statement of Attainment (prior to 2008 Certification of Attainment) for the course titled Sprayed Sealing Selection and Design.

- A statement signed by the Seal Designer that the seal design complies with the seal design method for the test results, assumptions and inputs used.

## 6.5.2	The Contractor shall price for this contract spray seals that use 10mm stones as detailed in Sections 6.5.3 and 6.5.4 below.

## 6.5.3	Unless otherwise specified, S10E binder shall be used in this Contract and the seal type shall be a Strain Alleviating Membrane (SAM).  For the purposes of estimating, the Contractor shall assume a binder spray rate of 1.2 to 1.8 L/m2 bitumen at 15ºC.

6.5.4	Unless otherwise specified, aggregates with a nominal size of 10mm shall be used for this Contract.  For the purposes of estimating, the contractor shall assume an aggregate spread rate of 110 to 160 m2/m3.

6.5.5	The Contractor shall, however, provide a rate only for the use 7mm and 14mm aggregates should the Superintendent direct to do so.  For the purposes of estimating, Contractor shall assume an aggregate spread rate of 200 to 250 m2/m3 for 7mm aggregates and 90 to 120 m2/m3 for 14mm aggregates.

6.5.6	Where directed by the Superintendent, the existing surface shall be crack sealed.  The Contractor shall nominate a proprietary product and sub-contractor to undertake this work and shall not proceed until approval is sought by the Superintendent.  This is a HOLD POINT to this Contract.

6.5.7	The Contractor shall measure the actual spread rate of aggregates by weighing the spreader trucks via a weighbridge upon each departure and arrival from the Contractor’s premises and calculating the difference.  This weight shall be converted to m3 based on the loose density of the stones and used to calculate a spread rate in m2/m3.  An allowance for excess stone shall also be made, reported and incorporated into the calculation for actual spread rate.  These calculations shall be submitted to the Superintendent prior to the subsequent day’s work within the Contract.  No subsequent surfacing works shall take place until the Superintendent is satisfied that the field spread rate matches the design spread rate for the project site and / or the Contractor demonstrates that they are able to take actions to better comply with the design spread rate and is a HOLD POINT to this Contract.

6.5.8	The Contractor shall prepare the pavement in accordance with the requirements of Section 8.6 of the specification.  All raised pavement markers shall also be removed.  The Superintendent shall inspect the prepared surface and spraying shall not commence until this is approved and is a HOLD POINT to the Contract.

6.5.9	Where excess stone is removed from site and reused, the stone shall be treated so as to once again conform to the requirements of the specification including, but not limited to, being clean and having the required precoat.

6.6	Dense Graded Asphalt

The contractor shall refer to the Northern Territory Government Standard Specification for Roadworks “9. DENSE GRADED ASPHALT” along with the following requirements which override any related provisions to the said specification:

6.6.1	The contractor shall price for this contract asphalt as per the requirements of the schedule of rates for Separable Portions 1, 2A and 2B and for all mix types  for periodic works under Separable Portion 3.

6.6.2	Unless otherwise specified, the following mix and binder types shall be as directed by the Superintendent:

- Mix Type 1	7 mm Aggregates	S10E Binder

- Mix Type 2	10 mm Aggregates	S10E Binder

- Mix Type 3	14 mm Aggregates	S10E Binder

- Mix Type 4	20 mm Aggregates	A15E Binder (Structural & Repair Layers)

- Mix Type 5	14 mm Aggregates	A15E Binder

6.6.3	For roads that have been profiled in preparation for resurfacing, the Contractor shall apply a heavy tack coat prior to sealing and / or asphalting.  Where required, a 7mm aggregate armour coat may also be applied.  All costs for this are deemed to be included in the contract rates for the various asphalt items.

6.6.4	Where directed by the Superintendent, the Contractor shall apply a SAMI seal prior to the placement of asphalt.  S10E binder shall be used at a minimum application rate of 1.6 L/m2 along with 10mm aggregates at 110 to 160 m2/m3, depending on aggregate ALD.

6.6.5	Where directed by the Superintendent, the Contractor shall undertake asphalt pavement repairs for both spray seal and asphalt works.  The Superintendent and the Contractor shall jointly identify areas and appropriate depths for pavement repairs prior to resurfacing taking place.

The area for pavement repairs shall be profiled (refer to Section 6.7 of this Technical Specification for cold milling requirements) with all edges made square and tack coat applied.  Mix Type 4 shall be used for pavement repairs with individual compacted layer depths no less than 50mm and no greater than 80mm.  Placement, compaction and conformance testing of the asphalt shall take place as per the requirements of the specification.

Measurement and payment for the asphalt pavement repairs shall be “per tonne” and evidenced by dockets issued by the asphalt plant.  All costs relating to the pavement repairs, are deemed to be included in the Contract rate.

6.6.6	The Contractor shall prepare the pavement in accordance with the requirements of the specification.  Where the surface treatment is an overlay of the existing surface, all raised pavement markers shall also be removed.  The Superintendent shall inspect the prepared surface and spraying shall not commence until this is approved and is a HOLD POINT to the Contract.

6.7	COLD MILLING Profile works

### 6.7.1	CONTROL OF WORK

### 6.7.1.1	Profiling Machine

Use a profiler machine capable of profiling a width of at least 1 metre for local roads and 2 metres for all other road types.

Profiling machine must meet ALL environmental requirements for dust suppression, noise etc.

6.7.1.2	Traffic

Full width profiling, kerb / edgeline to kerb, is to be completed prior to opening all lanes to traffic. No longitudinal steps will be permitted in profiled sections, except at intersection openings, which are to be chamfered at 1:2 using hot mix asphalt.

### 6.7.1.3	Variations

The Superintendent may direct the depth, width, length, alignment and section of road to be cold milled at any time.

### 6.7.1.4	Public Safety

The Superintendent may order work to cease temporarily on account of dust nuisance, excessive windrows or loose material, excessive roughness of the cold milled surface or any circumstances which the Superintendent considers may adversely affect the work or public safety.

### 6.7.2	COLD MILLING OPERATION

### 6.7.2.1	Control of Levels

The operation of the cold milling machine shall be controlled by automatic sensors unless otherwise approved by the Superintendent.

### 6.7.2.2	Variations in Cuts

The nominated depth(s) of cut of the cold milling machine shall be as directed by the Superintendent. The cut shall be automatically controlled, with the control set such that the maximum difference in levels between adjacent runs shall not exceed 5mm. The average depth of cut measured across the cut from the adjacent surfaces to the top of the milled surface and at intervals along the work shall not vary by more than 5mm from the specified thickness. When automatic sensors are used the top of the milled surface shall not vary by more than 5mm from the specified depth.

### 6.7.2.3	Utility Location

Prior to milling operations the Contractor shall determine, using appropriate equipment such as metal detectors etc, the location of any hidden utilities or buried objects that may be damaged by milling operations. The onus of locating such structures and determining their susceptibility to damage by operations are the sole responsibility of the Contractor. The Contractor shall liaise with the relevant Authorities for all underground utility services within the site of the works.

### 6.7.2.4	Unsuitable Material

If in the opinion of the Superintendent, the milled floor contains material that is deemed unsuitable, that material shall be milled to a depth as directed by the Superintendent. Payment shall be based upon a square metre rate commensurable as listed in the schedule.

### 6.7.2.5	Obstructions

When milling near access chambers or other similar structures the cold milling machine shall be operated as close as possible to the structure without causing damage to it. The remaining asphalt and base course shall be removed by hand or other method approved by the Superintendent. A ramp using cold mix or asphalt shall be formed and compacted around the structure. The ramp shall have a minimum taper length of 1.0m for each 50mm thickness of asphalt and base course removed or part thereof. This work shall not constitute a variation of contract.

### 6.7.2.6	Temporary Ramps

At the end of the day’s work, or whenever the milled pavement is left unattended and reopened to traffic, the work shall be arranged so that no longitudinal or transverse edges of milled asphalt and base course, which can affect traffic, are left unattended. Prior to reopening the milled pavement to unrestricted use by traffic and at the end of the day's work, the final milled lane shall be bevelled such that the maximum lip between the milled run and the unmilled run does not exceed 10mm. When bevelling is not possible, the falloff in levels shall be ramped with bituminous cold mix material.

### 6.7.2.7	Temporary Hot Mix

The ramp area covered by hot mix shall be tack coated with bitumen emulsion prior to placing of the hot mix. All hot mix shall be compacted.

### 6.7.2.8	Length of Ramps

Longitudinal and transverse ramps, used to tie the milled surface into the existing road levels, shall have a minimum taper length of 1m for each 50mm variation in levels or part thereof. Where the speed limit exceeds 60km/h, transverse ramps shall have a taper length of 2.5m for each 50mm.

### 6.7.2.9	Hand Work

Any material not removed by the cold milling machine adjacent to concrete medians, kerb and gutter or drainage structures such as pit grates shall be removed by hand or other means approved by the Superintendent. When necessary for traffic safety, or when directed by the Superintendent, hot mix or asphalt ramps shall be placed by the Contractor.

### 6.7.2.10 Additional Cuts

Any weakened planes of asphalt and base course which are not removed by the milling operation but in the opinion of the Superintendent will break up under traffic shall be removed either by an additional pass of the cold milling machine or by other means to the satisfaction of the Superintendent.

### 6.7.2.11	Loose Material

Following the cold milling operation all loose material shall be removed from the road pavement, gully pits and median areas. The pavement shall be swept and the site left in a clean and tidy state to the satisfaction of the Superintendent. All cold milled material shall be removed from the site and transported to stockpile site(s) or otherwise removed from the site to the satisfaction of the Superintendent.

### 6.7.2.12	Damage, Contractor’s Costs

If sub-surface utilities or structures are damaged by milling operations, the Contractor shall notify the relevant Authority and arrange for the damage to be rectified to reinstate the utility or structure to pre-construction condition. All costs associated with such rectification works shall be borne by the Contractor.

### 6.7.2.13	Inspection

Prior to covering the milled surface, the Contractor shall arrange to inspect the surface with the Superintendent prior to the removal of milling equipment from site.

### 6.7.3	TRANSPORT

### 6.7.3.1	Capacity of Trucks

The Contractor shall supply sufficient trucks to enable a continuous output to be achieved by the cold milling machine with minimal delay.

### 6.7.3.2	Loading and Covering of Trucks

When loading by elevator, the trucks shall back up and maintain a similar speed to the cold milling machine. The driver shall distribute the load of milled material uniformly over the truck body. The Contractor shall comply with all regulations regarding the covering and securing of loads where applicable. The cover shall overlap the truck body by at least 250mm and be tied down securely.

### 6.7.4	DISPOSAL OF MILLINGS

Unless directed by the Superintendent, all milled material shall be removed from site and disposed of by The Contractor.  Cost involved in the transport and disposal of the milled materials are deemed to be included in the unit rates for the Cold Milling items in the Schedule of Rates.

The Superintendent will advise if milled materials, for future re-use, are required by the City of Darwin, and the location of stockpiling of this material within the City of Darwin municipality.  Transport to the stockpile site is the responsibility of The Contractor and costs are deemed to be included in the unit rates for the Cold Milling items in the Schedule of Rates.

6.8	PAVEMENT MARKING

The Contractor shall refer to the Northern Territory Government Standard Specification for Roadworks “15. PAVEMENT MARKING” along with the following requirements which override any related provisions to the said specification.

6.8.1	The Contractor shall be responsible for recording, measuring and photographing all existing line marking prior to resurfacing activities taking place.  This information shall be provided to the Superintendent at least five (5) business days prior to works at each location and is a HOLD POINT to this Contract.  This information shall also be used for, but not limited to, defining asphalt pavement runs.

6.8.2	The Contractor shall install temporary raised pavement markers (stick and stomps) at the end of each day’s work where there was previously pavement markings delineating lanes and enforce regulations.  This includes, but not limited to, centre lines, lane lines, parking lanes, give way, stop lines and crossings.  These shall be maintained until such time road markings are reinstated.

6.8.3	The Contractor shall be responsible for the reinstatement of line marking for the specific projects in Separable Portions 1, 2A and 2B.  This reinstatement of line marking shall be costed as a lump sum amount.

6.8.4	The Principal shall be responsible for the reinstatement of the line marking for each work order in Separable Portion 3.

6.9	TRAFFIC SIGNAL DETECTOR LOOPS

The Contractor shall refer to the Northern Territory Government Standard Specification for Roadworks “18. TRAFFIC CONTROL SIGNALS” along with the following requirements which override any related provisions to the said specification.

6.9.1	Where resurfacing works occur near traffic signals, detector loops shall be replaced.  The Contractor shall engaged a suitably qualified electrical contractor to undertake this work and provide the Superintendent notice of the proposed electrical contractor prior to the commencement of works which is a Witness Point to this Contract.

6.9.2	All detector loops shall be installed in accordance with Northern Territory Government Standard Drawing CS-1507 and the plan detail in PART C - Attachments.  The Contractor shall take particular note of the requirement to profile an additional 30mm below the nominal asphalt thickness for placement of the loops.  Following placement and connection, this section shall have asphalt of the same specification placed and compacted to bring it back to the profiled surface level prior to the full asphalt resurfacing taking place.

6.9.3	The detector loops shall be the “PATRIOT LOOP” pre-fabricated type and be placed on the prepared surface and connected prior to the asphalt works commencing.  The Contractor shall be responsible for coordinating with the electrical contractor for these works.

6.9.4	The Contractor shall be responsible for liaising with the Department of Infrastructure, Planning and Logistics’ Traffic Section for advice of works taking place, access to the traffic signal controller and commissioning and testing of the installed detector loops.

6.9.5	All costs relating to the supply and installation of the traffic signal detector loops as required in this specification and the Northern Territory Government Standard Specifications are deemed to be included in the unit rate for the installation of each detector loop.

SECTION 7.00

TENDER DOCUMENTS

Please complete the separately attached Tender Return Forms and submit as part of tender response.

SECTION 8.00

ATTACHMENTS

8.00 ATTACHMENT A

8.00 ATTACHMENT B

VEHICLE DECAL SPECIFICATION

- General

The contractor shall only display the signs on their plant and equipment whilst servicing their contract with City Of Darwin.  One magnetic decal is to be displayed on each side of the contractor’s vehicle: i.e one decal to be displayed on the driver’s door or side panel and one decal to be displayed on the passenger door or side panel.

In the event that the decal becomes damaged or faded the Superintendent reserves the right to instruct the Contractor have that decal removed and replaced with a new decal.

The Contractor shall be liable for all costs incurred in the production and fitting of the specified decal.

Electronic version of the City Of Darwin logo and brand guidelines may be obtained by phoning the Contract Section on 08 89 30 0631.

Decal for the Contractors vehicles must be produced using the following specification.

- Logo And Text Specification

The colour logo should only be used on a light/white background. The colour logo should never be reproduced as a greyscale logo.

The City of Darwin typeface is Arial.

VEHICLE DECAL SPECIFICATION - continued

- Sign Size

The sign shall be 400mm wide x 300mm high.

- Example

Typical design of decal to be displayed on Contractors vehicle at Figure 1.

Figure 1.

Requests for variations to the specified decal must be in writing to the Superintendent and shall not be deemed to be approved unless written approval is received from the Superintendent.

SECTION 9.00

APPENDIX

Part A 		Separable Portions (TO BE COMPLETED)

| Clause 1 | Separable Portion Number | 1 |
| --- | --- | --- |
| Clause 1 | Description of Separable Portion | Separable Portion 1 Cavenagh Street (Stage 1) |
| Item 7 a) b) | Date for Practical Completion or Period of time for Practical completion | 27 September 2019 |
| 13 a) b) d) e) f) g) | Contractors security Form Amount Time for provision (except for retention monies) Additional security for unfixed plant and materials Contractor’s security returned upon certificate of practical completion Contractor’s security retained upon certificate of practical completion | Unconditional Bank Guarantee Amount held for entire Contract Prior to issue of Possession of Site Certificate Not applicable Nil 100% Note: Security will be released as per Section 4 Annexure when all works under the Contract are complete. |
| 14 | Principal’s security | Not applicable |
| 24 | Liquidated damages rate | Not applicable |
| 25 a) b) | Bonus for early practical completion Rate Limit | Not applicable |
| 26 | Delay damages, other compensable causes | Nil |

| Clause 1 | Separable Portion Number | 2 |
| --- | --- | --- |
| Clause 1 | Description of Separable Portion | Separable Portion 2 Cavenagh Street (Stage 2) & Daly Street |
| Item 7 a) b) | Date for Practical Completion or Period of time for Practical completion | 29 May 2020 |
| 13 a) b) d) e) f) g) | Contractors security Form Amount Time for provision (except for retention monies) Additional security for unfixed plant and materials Contractor’s security returned upon certificate of practical completion Contractor’s security retained upon certificate of practical completion | Unconditional Bank Guarantee Amount held for entire Contract Prior to issue of Possession of Site Certificate Not applicable Nil 100% Note: Security will be released as per Section 4 Annexure when all works under the Contract are complete. |
| 14 | Principal’s security | Not applicable |
| 24 | Liquidated damages rate | Not applicable |
| 25 a) b) | Bonus for early practical completion Rate Limit | Not applicable |
| 26 | Delay damages, other compensable causes | Nil |

| Clause 1 | Separable Portion Number | 3 |
| --- | --- | --- |
| Clause 1 | Description of Separable Portion | Separable Portion 3 Periodic Work |
| Item 7 a) b) | Date for Practical Completion or Period of time for Practical completion | As directed by Superintiendent |
| 13 a) b) d) e) f) g) | Contractors security Form Amount Time for provision (except for retention monies) Additional security for unfixed plant and materials Contractor’s security returned upon certificate of practical completion Contractor’s security retained upon certificate of practical completion | Unconditional Bank Guarantee Amount held for entire Contract Prior to issue of Possession of Site Certificate Not applicable Nil 100% Note: Security will be released as per Section 4 Annexure when all works under the Contract are complete. |
| 14 | Principal’s security | Not applicable |
| 24 | Liquidated damages rate | Not applicable |
| 25 a) b) | Bonus for early practical completion Rate Limit | Not applicable |
| 26 | Delay damages, other compensable causes | Nil |