**Community Grants example project plan**

Project: Language playgroup

|  |  |  |
| --- | --- | --- |
| **What** | **When** | **Who** |
| Venue booking | December | Volunteer committee |
| Contact potential facilitators and confirm | January | Volunteer committee |
| Research and purchase reading resources | December - January | Volunteer committee |
| Promotional posters   * Create and distribute | January and April | Volunteer committee |
| Promotion via social media | January - June | Volunteer committee |
| Promotion via newsletter | January - June | Volunteer committee |
| Book equipment:   * Baby gym * Sound equipment | January | Volunteer committee |
| Language playgroup sessions | Terms 1 and 2 | 1 x paid facilitator |
| Prepare parent survey for final session | May | Volunteer committee |
| Debrief | July | Volunteer committee |
| Acquittal | October | Volunteer committee |