# Community Grants Example Project Plan — Timeline

### (What / When / Who)

Best for events and projects with clear, sequential steps.

List each activity or step, when it will happen, and who is responsible. Timing and responsibility are how you show the project is viable, which is one of the two things City of Darwin assesses. Delete the example rows and fill in your own, or start from the blank table below. Add or remove rows as you need.

## Example: Language playgroup

| What | When | Who |
| --- | --- | --- |
| Venue booking | December | Volunteer committee |
| Contact potential facilitators and confirm | January | Volunteer committee |
| Research and purchase reading resources | December to January | Volunteer committee |
| Create and distribute promotional posters | January and April | Volunteer committee |
| Promotion via social media and newsletter | January to June | Volunteer committee |
| Book equipment (baby gym, sound equipment) | January | Volunteer committee |
| Run language playgroup sessions | Terms 1 and 2 | 1 x paid facilitator |
| Prepare parent survey for final session | May | Volunteer committee |
| Debrief | July | Volunteer committee |
| Acquittal | October | Volunteer committee |

Your project plan

| What | When | Who |
| --- | --- | --- |